STANDARD BIDDING DOCUMENT

Procurement of Works

Small Contracts

###### His Majesty’s Government of Nepal

January 2002

# Table of Contents

Introduction and Instructions	1

Section I.	Invitation for Bids	3

Section II.	Instructions to Bidders	5

Section III.	Forms of Bid, Qualification Information, Letter of Acceptance, Agreement and Appendix	11

Section IV.	General Conditions of Contract	19

Section V.	Particular Conditions	29

Section VI.	Forms of Securities	30

Section VII.	Specification	34

Section VIII.	Drawings	35

Section IX.	Bill of Quantities	36

Section X.	Rules for Adjudication	37

Section XI.	Notes for Guidance	42

Introduction and Instructions

1.	Use of Standard Bidding Documents for Procurement of Works

The following Standard Bidding Documents (SBD) have been prepared for use by HMGN in the procurement of works:

Procurement of Works – Large Contracts

For use in international competitive bidding (ICB) and international shopping/limited international bidding (LIB) for most building and engineering works in Nepal.  Normally the Employer and the Donor Agency jointly decide which project works will be bid under ICB and which will be bid under national or local competitive bidding (NCB/LCB) depending upon on the size and complexity of the works and the capacity of the domestic contracting industry.  All ICB works will use the Large Works SBD.  The language is English.

The Large Works SBD may also be used in NCB/LCB in exceptional circumstances where the value of the works is very high (e.g. greater than NRs. 500 million) and justifies the more elaborate conditions contained in the Large Works SBD.

Procurement of Works – Medium Contracts:

For use in NCB/LCB for building and engineering works greater than NRs. 10 million.  The language is English.

Procurement of Works – Small Contracts:

For use in NCB/LCB for building and engineering works up to NRs. 30 million.  The language is Nepali or English.

There is an overlap between the SBDs for Small and Medium Contracts in the range NRs. 10 to 30 million where the selection of document to be used will depend on the complexity of the works.

The three SBDs are intended for building and engineering works designed by the Employer or his consultant in which the method of payment is remeaurement of quantities.  These SBDs are not suitable for the procurement of electrical and/or mechanical plant under design-build and turnkey contractual arrangements. Other bidding documents such as the FIDIC Conditions of Contract for Plant and Design-Build Contracts or Conditions of Contract for Engineering, Procurement and Construction/Turnkey Projects should be used in these applications.

2.	General Instructions

All documents listed in the table of contents, excluding these Introduction and Instructions, are normally required for the procurement of works.  However, they should be adapted as necessary to the circumstances of each project.

The italicized text in the Notes boxes, remarks in [ ] brackets and footnotes contain instructions to the user and are not part of the SBD.  They should be deleted from the documents issued to bidders.

Each SBD contains standard Instructions to Bidders and General Conditions of Contract which have been developed and proven in international applications over many years and should remain unchanged.  Users should add project-specific information or special conditions of contract in the Bidding Data, Contract Data, Appendices and Particular Conditions of Contract as applicable.

Standard Prequalification Document – Prequalification of Contractors: each SBD may be used with either prequalification or post-qualification of bidders.  Users may choose to this Standard Prequalification Document or the qualification forms contained in the SBDs.  Whichever method is used, bidders must provide up-to-date qualification information to permit valid evaluation of bids.

Standard Guide for Bid Evaluation: provides bid evaluation procedures and forms for determining the lowest substantially responsive evaluated bid price from bids received using these SBDs.

The SBDs are intended to complement the bidding, bid evaluation and award of contract procedures contained in PWD Part II Chapter 9 Procurement of Works.

3.	Additional Information on the SBD Procurement of Works – Small Contracts

This SBD is based on the FIDIC Short Form of Contract, First Edition 1999. The General Conditions are unchanged.  The FIDIC form of Agreement has been replaced by separate forms of Invitation for Bids and Agreement.  Instructions to Bidders have been added in conformance with HMGN procedures and have been approved by the Financial Comptroller General’s Office.

The SBD is available in both English and Nepali versions. The Nepali version is intended to permit all domestic contractors to fully understand the conditions of contract, and to be the principal SBD for small building and civil works in Nepal.  The English version is intended primarily to provide donors and international consultants with a translation of the Nepali document.  The English version may be used if required by donors or the circumstances of a particular project, but users must choose one or other version as the basis for the bids and contract.

The SBD is simple and straightforward, enabling experienced Project Managers to prepare the bidding documents in their offices without consultant assistance.

Section I.	Invitation for Bids

Notes on the Invitation for Bids The Invitation for Bids shall be issued as: (a) an advertisement in at least one newspaper of national circulation in Nepal for two days; (b) an advertisement displayed on the Notice Board of the office inviting the bids; and (c) an advertisement forwarded to the following offices for display on their notice boards: - District Administration Office - Land Revenue Office - District Development Committee - District Treasury Comptroller Office - Offices of the contractors, if any, at the headquarters of a district. Its purpose is to supply information to enable potential Bidders to decide on their participation. Apart from the essential items listed in the sample documents, the Invitation for Bids should also indicate any important bid evaluation criteria. The Invitation for Bids may be incorporated in the bidding documents for the record, or it may be omitted. In either event, the information contained in the Invitation for Bids should conform to the bidding documents and, in particular, to the relevant information in the Appendix to be attached herein.

Invitation for Bids

His Majesty's Government of Nepal

[name of Employer]

Date: _______________

Name of Project: _________________

Name of Contract: ________________

Contract Identification No: __________________

Name of the Donor Agency [if applicable]: ______________________

Donor Loan/Credit/Grant No [if applicable]: ______________________

- The [name of Employer] invites sealed bids from registered class [specify class] contractors for the construction of [brief description of the Works].

- Eligible Bidders may obtain further information and inspect the bidding documents at the office of [name, location, mailing address, telephone and facsimile numbers and email address of project office].

- Bidding documents may be purchased by eligible Bidders on the submission of a written application attaching copies of the Bidder’s registration, VAT registration and tax clearance certificate and upon payment of a non-refundable fee of [amount in Nepali Rupees].

- Bids must be submitted to the above office on or before [time] on [date]. Documents received after this deadline will not be accepted.

- Bids will be opened in the presence of Bidders' representatives who choose to attend at [time and date] at the office of [address and appropriate office].

- Bids must be valid for a period of [days] after bid opening and must be accompanied by security of [amount in Nepali Rupees].

- If the last date of purchasing, submission and opening falls on a government holiday then the next working day shall be consider the last day.

- Bidders are advised to visit site and assess the actual site conditions before submitting their bid.

Section II.	Instructions to Bidders

Notes on the Instructions to Bidders This section of the bidding documents should provide the information necessary for Bidders to prepare responsive bids, in accordance with the requirements of the Employer. It should also give information on bid submission, opening and evaluation, and award of Contract. These Instructions to Bidders will not be part of the Contract and will cease to have effect once the Contract is signed.

Instructions to Bidders

#### A.  General

| 1. Scope of Works | The Employer invites bids for the contraction of works as detailed in attached specifications, drawings and the bill of quantities herein. The successful Bidder is expected to complete the works as mentioned in the Bidding Data. |
| --- | --- |
| 2. Eligible Bidder | This Invitation for Bids is open to all registered contractors with qualifications as described in the Bidding Data. |
| 3. One Bid per Bidder | Each Bidder shall submit only one bid. No alternative bid shall be accepted. |
| 4. Qualification of the Bidder | All Bidders shall provide Qualification Information in Section III. To qualify for award of the Contract, Bidders shall meet the following minimum qualifying criteria: - average annual volume of construction work in the last five years of at least the amount specified in the Bidding Data; - successful experience as prime contractor in the construction of at least two works of a nature and complexity equivalent to the Works in the last ten years (to comply with this requirement, works cited should be at least 70 percent complete); - proposals for the timely acquisition (own, lease, hire, etc.) of the essential equipment listed in the Bidding Data; - a Contract Manager with five years’ experience in works of an equivalent nature and volume, including no less than three years as a Contract Manager; and - liquid assets and/or credit facilities, net of other contractual commitments and exclusive of any advance payments which may be made under the Contract, of no less than the amount specified in the Bidding Data. |
| 5. Cost of Bidding | The Bidder shall bear all costs associated with the preparation and submission of his bid and the Employer will in no case be liable for those costs. |
| 6. Site Visit | The Bidder at his own cost, responsibility and risk may visit the site of the works and acquire all necessary information for preparing the bid and entering into a contract for construction of the works. |
| 7. Content of Bidding Documents | The Bidding Documents comprise the documents listed below: - Invitation for Bids - Instructions to Bidders - Bidding Data - Form of Bid and Qualification InformationAgreement, Bid, Acceptance, appendix - Agreement and Appendix - General Conditions of Contract - Particular Conditions of Contract - Securities Forms: Bid, Performance, Advance Payment - Specification - Drawings - Bill of Quantities |
| 8. Clarification of Bidding Documents | A prospective Bidder may request clarification on the bidding documents in writing and the Employer will respond to such request. Copies of the response will be forwarded to all the purchasers of the bidding documents. |
| 9. Language of Bid | All documents relating to the bid shall be in English or in Nepali. |
| 10. Documents Comprising Bid | The bid by the Bidder shall comprise the following: - Bid and Qualification Information - Bid Security - Priced Bill of Quantities - Rate Analysis (optional at request of Employer) |
| 11. Bid Prices | The contract shall be for the whole works described in scope of works based on the priced Bill of Quantities submitted by the Bidder. The Bidder shall fill in rates and prices for all items of the works in Nepali Rupees. Items for which no rate or price is entered shall be deemed covered by the other rates and prices in the Bill of Quantities and will not be paid by the Employer. All duties, taxes and other levies payable by the contractor under the contract shall be included in the rates, prices and total Bid Price submitted by the Bidder. |
| 12. Bid Validity | The bid shall remain valid for the period specified in the Bidding Data. |
| 13. Bid Security | The Bidder shall furnish a Bid Security in Nepali Rupees in the amount specified in the Bidding Data. The Bid Security shall remain valid for a period of 28 days beyond the original validity period for bid and any period of extension subsequently requested by the employer. The Bid Security shall be in the form of a bank guarantee from a bank acceptable to the Employer or a cash voucher deposited in the Bank Account of the Employer specified in the Bidding Data. |
| 14. Formal and Signing of Bids | One original and one duplicate copy of the bid shall be typed or written in indelible ink and shall be signed by an authorized person. Any entries or amendments including alternations, additions or corrections made shall be initialled by the same authorized person. |
| 15. Sealing and Marking of Bids | The Bidder shall seal one original and one duplicate copy of the bid in inner and outer envelopes. The envelopes shall be addressed to the Employer at the address provided in the Bidding Data and bear the name and identification number of the contract. |
| 16. Deadline for Submission of Bids | Bids shall be delivered to the Employer at the address no later than the time and date specified in the Bidding Data. |
| 17. Late Bids | Any bid received by the Employer after the deadline will not be accepted and will be returned unopened to the Bidder. |
| 18. Bid Opening | The Employer will open the bids in the presence of the Bidders' representatives who choose to attend at the time and in the place specified in the Bidding Data. The Bidders' names, the total amount of each bid, any discounts, the presence or absence of Bid Security and such other details as the Employer may consider appropriate will be announced by the Employer at the opening. The Employer will prepare and provide minutes of the bid opening including the information disclosed to those present. |
| 19. Evaluation and Comparison of Bids | The Employer will evaluate and compare only the bids determined to be substantially responsive meeting all the conditions specified in the bidding documents. In evaluating the bids, the Employer will determine for each bid the evaluated Bid Price by taking into account any correction for errors or making an appropriate adjustment for any other acceptable variations, deviations or discount. |
| 20. Process to be Confidential | Information relating to the examination, clarification, evaluation and comparison of bids and recommendations for the award of a contract shall not be disclosed to Bidders or any other persons not officially concerned with such process until the award to the successful Bidder has been announced. Any effort by a Bidder to influence the Employer’s processing of bids or award decisions may result in the rejection his bid. |
| 21. Award of Contract | The Employer will award the contract to the Bidder whose bid has been determined to be substantially responsive to the bidding documents and who has offered the lowest evaluated Bid Price, provided that such Bidder has been determined to be eligible and qualified in accordance with the provisions of clauses 2 and 4. |
| 22. Employer's Right to Accept any Bid and to Reject any or all Bids | The Employer reserves the right to accept or reject any bid and to cancel the bidding process and reject all bids, at any time prior to the award of the contract, without thereby incurring any liability to the affected Bidder or Bidders. |
| 23. Notification of Award and Signing of Agreement | The Bidder whose bid is accepted will be notified of the award by the Employer prior to the expiration of the bid validity period. This notification (hereafter called the “Letter of Acceptance”) will state the sum that the Employer will pay the Bidder in consideration of the execution, completion, and maintenance of the works as prescribed by the contract. The Agreement between the Employer and the successful Bidder will be signed by the Employer and sent to the successful Bidder within 28 days following the issuance of the Letter of Acceptance. Within 7 days of receipt, the successful Bidder will sign the Agreement and deliver it to the Employer. |
| 24. Performance Security | Within 14 days after receipt of the Letter of Acceptance, the successful Bidder shall deliver to the Employer a Performance Security in the amount stipulated in the Appendix. |

Bidding Data

This Bidding Data is not a part of the Agreement

| Item | Clause | Data |
| --- | --- | --- |
| Scope of the Works | 1 | [provide details] |
| Eligible Bidder | 2 | Registered class ……..of contractor |
| Minimum requirement of average annual turnover in the last five years | 4 (a) | [insert amount in Nepalese Rupees] |
| Requirement of minimum equipment | 4 (c) | [the essential equipment to be made available for the Contract by the successful Bidder shall be as mentioned in Section III, Sub-clause 1.4] |
| Minimum requirement of liquid assets and/or credit facilities | 4 (e) | [insert amount in Nepalese Rupees] |
| Deadline for requesting clarification of bidding documents | 8 | 7 days prior to bid Opening date |
| Language of bid | 9 | [English or Nepali] |
| Documents comprising the bid are: - Bid and Qualification Information - Bid Security - Priced Bill of Quantities - Rate Analysis (optional at request of Employer) |  |  |
| Bid validity period | 12 | [insert number of days, multiple of seven] |
| Bid security | 13 | [insert an amount or a percentage of total Bid Price] |
| Deadline and location for submitting bid | 16 | [provide time, date and place] |
| Bid opening date | 18 | [provide time, date and place] |
| Bank Account of Employer | 13 | [provide details] |
| Address of Employer | 15 | [provide details] |

Section III.	Forms of Bid, Qualification Information, Letter of Acceptance, Agreement and Appendix

Notes on Forms of Bid, Qualification Information, Letter of Acceptance, Agreement and Appendix The Agreement should incorporate any corrections or modifications to the bid resulting from corrections of errors, price adjustment during the evaluation process, acceptable deviations or any other mutually-agreeable changes allowed for in the General Conditions. The bid which the contractor has submitted to the Employer becomes part of the contract documents. All the information in regards to the preparation of bid to meet the Employer's requirements shall be provided before issuing the bidding documents. The contractor shall provide the remaining information by completing the form.

Bid

We have examined the documents listed in the Appendix and offer to execute the Works in conformity with the Contract for the sum of ……………………. ………………………….. (in words) ……………………………………………………………………… ………………………….. (in figures) or such other sum as may be ascertained under the contract.

This bid is submitted in one original and one duplicate copy.

This bid shall remain binding until ___________ [date]. This bid and your written acceptance of it shall constitute a binding contract between us.

We understand that the Employer is not bound to accept the lowest or any offer received for the Works.

Signature _____________________________	Date: _________________________________

Name : _______________________________	Authorised to sign on behalf of (organisation name): _______________________________

- Designation: ______________________

- Office Stamp of the Organisation: ____________________________________

## Qualification Information

Notes to Bidders The information to be filled in by Bidders in the following pages will be used for purposes of postqualification as provided for in Clause 4 of the Instructions to Bidders. This information will not be incorporated in the Contract. Attach additional pages as necessary.

1.	Individual Bidders or Individual Members of Joint Ventures

1.1	Constitution or legal status of Bidder:  [attach copy]

Place of registration:  [insert]

Principal place of business:  [insert]

Power of attorney of signatory of Bid:  [attach]

  - Total annual volume of construction work performed in the past five years, in NRs.

| Annual turnover data (construction only) |  |
| --- | --- |
| Year | Turnover in NRs. |
| 1. |  |
| 2. |  |
| 3. |  |

1.3	Work performed as prime contractor on works of a similar nature and volume over the last ten years.  Also list details of work under way or committed, including expected completion date.

| Project Name | Name of Employer and contact person | Type of work performed and year of completion | Total Value of Contract | Value of remaining work |
| --- | --- | --- | --- | --- |
| 1. |  |  |  |  |
| 2. |  |  |  |  |

1.4	Major items of contractor’s Equipment proposed for carrying out the Works.  List all information requested below.

| Item of equipment | Description, make, and age (years) | Owned, leased (from whom?), or to be purchased (from whom?) |
| --- | --- | --- |
| 1. [Employer to specify equipment requirements] |  |  |
| 2. |  |  |

1.5	Qualifications and experience of Contract Manager proposed for administration and execution of the Contract.  Attach bio-data.

| Name | Years of experience (general) | Years of experience in proposed position |
| --- | --- | --- |
| 1. |  |  |
| 2. |  |  |

1.6	Evidence of access to financial resources to meet the qualification requirements: cash in hand, lines of credit, etc. List below and attach copies of support documents.

| Source of financing | Amount in NRs |
| --- | --- |
| 1. |  |
| 2. |  |
| 3. |  |

2.	Joint Ventures

2.1	The information listed in 1.1 - 1.6 above shall be provided for each partner of the joint venture.

2.2	Attach the power of attorney of the signatory(ies) of the bid authorising signature of the bid on behalf of the joint venture.

2.3	Attach the Agreement among all partners of the joint venture (and which is legally binding on all partners), which shows that

(a)	all partners shall be jointly and severally liable for the execution of the Contract in accordance with the Contract terms;

(b)	one of the partners will be nominated as being in charge, authorized to incur liabilities, and receive instructions for and on behalf of any and all partners of the joint venture; and

(c)	the execution of the entire Contract, including payment, shall be done exclusively with the partner in charge.

## Letter of Acceptance

[letterhead of the Employer]

Date: ________________________

To:  [name and address of the contractor]

This is to notify you that your bid dated [date] for execution of the [name of the Contract and identification number, as given in the Invitation to Bid] for the Contract Price of [insert the amount in Nepalese Rupees in numbers and words] as corrected and modified in accordance with the Instructions to Bidders is hereby accepted by our Agency.

You are hereby instructed to come to our office [Office address] to sign the formal agreement on [date] at [time].

Authorised Signature:

Name:

Designation:

Agreement

This Agreement, made the [day] day of [month], [year] between [name and address of Employer] (hereinafter called “the Employer”) and [name and address of contractor] (hereinafter called “the contractor”) of the other part.

Whereas the Employer is desirous that the contractor execute [name and identification number of contract] (hereinafter called “the Works”) and the Employer has accepted the bid for ________________ [insert the amount in Nepalese Rupees in numbers and words] by the contractor for the execution and completion of such Works and the remedying of any defects therein.

Now this Agreement witnesseth as follows:

1.	In this Agreement, words and expressions shall have the same meanings as are respectively assigned to them in the Conditions of Contract hereinafter referred to, and they shall be deemed to form and be read and construed as part of this Agreement.

2.	In consideration of the payments to be made by the Employer to the contractor as hereinafter mentioned, the contractor hereby covenants with the Employer to execute and complete the Works and remedy any defects therein in conformity in all respects with the provisions of the Contract.

3.	The Employer hereby covenants to pay the contractor in consideration of the execution and completion of the Works and the remedying of defects wherein, the Contract Price or such other sum as may become payable under the provisions of the Contract at the times and in the manner prescribed by the Contract.

In Witness whereof the parties thereto have caused this Agreement to be executed the day and year first before written.

The Common Seal of

was hereunto affixed in the presence of:

Signed, Sealed, and Delivered by the said

in the presence of:

Binding Signature of Employer

Binding Signature of Contractor

[Addendum showing the corrections if any made during the bid evaluation should be attached with this agreement]

Appendix

This Appendix forms part of the Agreement

[Note : with the exception of the items for which the Employer's requirements have been inserted, the Bidder shall complete the following information before submitting his bid.]

| Item | Clause | Data |
| --- | --- | --- |
| Documents forming the Contract listed in the order of priority | 1.1.1 |  |
| Document (delete if not applicable) - The Agreement - Particular Conditions - General Conditions - The Specification - The Drawings - The contractor's tendered design (if any) - The Bill of Quantities - …………………………...(if any) - ……………………………(if any) |  | Document Identification |
| Time for Completion | 1.1.12 | ………….days |
| Law of Contract | 1.4 | Applicable Law of Nepal |
| Language | 1.5 | English or [in Nepali version] |
| Provision of Site | 2.1 | On the commencement date* |
| Authorised person | 3.1 | ………………………………….. |
| Name and address of Employer's representative (if known) | 3.2 | …………………………………... |
| Performance security (if any): Amount Form | 4.4 4.4 | ……. % of the contract price Attached in section VI |
| Requirements for contractor’s design (if any) | 5.1 | Specification Clause No’s……. |
| Time for the submission of programme | 7.2 | Within 14 days* of the commencement date |
| Amount payable due to failure to complete | 7.4 | …………… per day up to a maximum of 10%* of sum stated in the Agreement |
| Period for notifying defects | 9.1 & 11.5 | 365 days* calculated from the date stated in the notice under Sub-Clause 8.2. |
| Variation procedure* Daywork rates | 10.2 | ………………………….(details) |

| Valuation of the Works* |  |  |  |  |
| --- | --- | --- | --- | --- |
| Lump sum price |  | 11.1 | …………………………(details) |  |
| Lump sum price with schedules of rates |  | 11.1 | …………………………(details) |  |
| Lump sum price with bill of quantities |  | 11.1 | …………………………(details) |  |
| Remeasurement with bid bill of quantities |  | 11.1 | ………………………..(details) |  |
| Cost reimbursable |  | 11.1 | …………………………(details) |  |
| Percentage of value of Materials and Plant |  | 11.2 | Materials ………% Plant …………..% |  |
| Percentage of retention |  | 11.3 | 5% of Contract Price |  |
| Currency of payment |  | 11.7 | Nepalese Rupees |  |
| Rate of interest |  | 11.8 | ………………. % per annum |  |
| Advance Payment |  | 11.9 | ……..% of the contract price |  |
| Arbitration |  |  |  |  |
| Rules |  | 15.3 | Nepal Council of Arbitration (NEPCA) |  |
| Appointing Authority |  | 15.3 | President, NEPCA |  |
| Place of Arbitration |  | 15.3 | Nepal |  |
| Insurances | 14 |  |  |  |
| Type of cover* | Amount to cover* |  |  | Exclusions* |
| The Works, Materials, Plant and fees | The sum stated in the Agreement plus 15% |  |  |  |
| Contractor's Equipment | Full replacement cost |  |  |  |
| Third Party injury to persons and damage to property | ………………. |  |  |  |
| Workers | ………………. |  |  |  |
| Other cover* | ………………. |  |  |  |

* Employer to specify as appropriate

Section IV.	General Conditions of Contract

| 1. General Provisions |  |
| --- | --- |
| 1.1 Definitions | In the Contract as defined below, the words and expressions defined shall have the following meanings assigned to them, except where the context requires otherwise: |
| The Contract | 1.1.1 “Contract” means the Agreement signed between the Employer and the contractor and the other documents listed in the Appendix. - “Specification” means the document as listed in the Appendix, including Employer’s requirements in respect of design to be carried out by the contractor, if any, and any Variation to such document. - “Drawings” means the Employer’s drawings of the Works as listed in the Appendix, and any Variation to such drawings. - “Bill of Quantities” means the priced and completed bill of quantities forming part of the Tender. - “Bid or Tender” means the contractor’s priced offer to the Employer for the execution and completion of the Works and the remedying of any defects therein in accordance with the provisions of the Contract, as accepted by the Letter of Acceptance. - “Letter of Acceptance” means the formal acceptance by the Employer of the bid or Tender. |
| Persons | - “Employer” means the person named in the Agreement and the legal successors in title to this person, but not (except with the consent of the contractor) any assignee. - “Contractor” means the person named in the Agreement and the legal successors in title to this person, but not (except with the consent of the Employer) any assignee. - “Party” means either Employer or the contractor. |
| Date, Times and Periods | - "Commencement Date" means the date 14 days after the date the Agreement comes into effect or any other date agreed between the Parties. - "Day " means a calendar day. - "Time for Completion" means the time for completing the Works as stated in the Appendix (or as extended under Sub-Clause 7.3), calculated from the Commencement Date. |
| Money and Payments | - "Cost" means all expenditure properly incurred (or to be incurred) by the contractor, whether on or off the Site, including overheads and similar charges, but does not include profit. - “Contract Price” means the sum stated in the Letter of Acceptance as payable to the contractor for the execution and completion of the works and the remedying of any defects therein in accordance with the provisions of the Contract. - “Retention Money” means the aggregate of all monies retained by the Employer pursuant to Sub-Clause 11.3. |
| Other Definitions | - “Contractor's Equipment" means all apparatus, machinery, vehicles, facilities and other things required for the execution of the Works but does not include Materials or Plant. - "Country" means Nepal. - "Employer's Liabilities" means those matters listed in Sub-Clause 6.1. - "Force Majeure" means an exceptional event or circumstance: which is beyond a Party's control; which such Party could not reasonably have provided against before entering into the Contract; which, having arisen, such Party could not reasonably have avoided or overcome; and, which is not substantially attributable to the other Party. - "Materials" means things of all kinds (other than Plant) intended to form or forming part of the permanent work. - "Plant" means the machinery and apparatus intended to form or forming part of the Permanent Works. - "Site" means the places provided by the Employer where the Works are to be executed, and any other places specified in the Contract as forming part of the Site. - "Variation" means a change to the Specification and/or Drawings (if any) which is instructed by the Employer under Sub-Clause 10.1. - "Works" means all the work and design (if any) to be performed by the contractor including temporary work and any Variation. - “Permanent Works” means the permanent works to be executed (Including Plant) in accordance with the Contract. - “Temporary Works” means all temporary works of every kind (other than contractor’s Equipment) required in or about the execution and completion of the Works and the remedying of any defects therein. - “Adjudication” means the procedure to be adopted by the contractor and the Employer in solving the dispute if it is not solved amicably pursuant to Sub-Clause 15.1. |
| 1.2 Interpretation | Words importing persons or parties shall include firms and organisations. Words importing singular or one gender shall include plural or the other gender where the context requires. |
| 1.3 Priority of Documents | The documents forming the Contract are to be taken as mutually explanatory of one another. If an ambiguity or discrepancy is found in the documents, the Employer shall issue any necessary instructions to the contractor, and the priority of the documents shall be in accordance with the order as listed in the Appendix. |
| 1.4 Law | The law of the Contract is stated in the Appendix. |
| 1.5 Communications | Where provision is made for the giving or issue of any notice, instruction, or other communication by any person, unless otherwise specified such communication shall be written in the language stated in the Appendix as shall not be unreasonably withheld or delayed. |
| 1.6 Statutory Obligations | The contractor shall comply with the laws of the countries where activities are performed. The contractor shall give all notices and pay all fees and other charges in respect of the Works. |
| 2. The Employer |  |
| 2.1 Provision of Site | The Employer shall provide the Site and right of access thereto at the times stated in the Appendix. |
| 2.2 Permits and Licenses | The Employer shall, if requested by the contractor, assist him in applying for permits, licences or approvals which are required for the Works. |
| 2.3 Employer's Instructions | The contractor shall comply with all instructions given by the Employer in respect of the Works including the suspension of all or part of the Works. |
| 2.4 Approvals | No approval or consent or absence of comment by the Employer or the Employer's representative shall affect the contractor's obligations. |
| 3. Employer's Representatives |  |
| 3.1 Authorised Person | One of the Employer's personnel shall have authority to act for him. This authorised person shall be as stated in the Appendix, or as otherwise notified by the Employer to the contractor. |
| 3.2 Employer's Representative | The Employer may also appoint a firm or individual to carry out certain duties. The appointee may be named in the Appendix, or notified by the Employer to the contractor from time to time. The Employer shall notify the contractor of the delegated duties and authority of this Employer's representative. |
| 4. The Contractor |  |
| 4.1 General Obligations | The contractor shall carry out the Works properly and in accordance with the Contract. The contractor shall provide all supervision, labour, Materials, Plant and contractor's Equipment which may be required. All Materials and Plant on Site shall be deemed to be the property of the Employer. During continuance of the of the contract, the contractor and his sub-contractors shall abide at all times by all labour laws, including child labour related enactments, and rules made thereunder. A child who has not attained the age of fourteen years shall not be employed in any work as a labourer. |
| 4.2 Contractor's Representative | The contractor shall submit to the Employer for consent the name and particulars of the person authorised to receive instructions on behalf of the contractor. |
| 4.3 Subcontracting | The contractor shall not subcontract the whole of the Works. The contractor shall not subcontract any part of the Works without the consent of the Employer. |
| 4.4 Performance Security | If stated in the Appendix, the Contractor shall deliver to the Employer no later than the date specified in the Letter of Acceptance. |
| 5. Design by Contractor |  |
| 5.1 Contractor's Design | The contractor shall carry out design to the extent specified, as referred to in the Appendix. The contractor shall promptly submit to the Employer all designs prepared by him. Within 14 days of receipt the Employer shall notify any comments or, if the design submitted is not in accordance with the Contract, shall reject it stating the reasons. The contractor shall not construct any element of the permanent work designed by him within 14 days after the design has been submitted to the Employer or where the design for that element has been rejected. Design that has been rejected shall be promptly amended and resubmitted. The contractor shall resubmit all designs commented on taking these comments into account as necessary. |
| 5.2 Responsibility for Design | The contractor shall remain responsible for his tendered design and the design under this Clause, both of which shall be fit for the intended purposes defined in the Contract and he shall also remain responsible for any infringement of any patent or copyright in respect of the same. The Employer shall be responsible for the Specification and Drawings. |
| 6. Employer's Liabilities |  |
| 6.1 Employer’s Liabilities | In this Contract, Employer's Liabilities mean: - war, hostilities (whether war be declared or not), invasion, act of foreign enemies, within the Country, - rebellion, terrorism, revolution, insurrection, military or usurped power, or civil war, within the Country, - riot, commotion or disorder by persons other than the contractor's personnel and other employees, affecting the Site and/or the Works, - ionising radiations, or contamination by radio-activity from any nuclear fuel, or from any nuclear waste from the combustion of nuclear fuel, radio-active toxic explosive, or other hazardous properties of any explosive nuclear assembly or nuclear component of such an assembly, except to the extent to which the contractor may be responsible for the use of any radio-active material, - pressure waves caused by aircraft or other aerial devices travelling at sonic or supersonic speeds, - use or occupation by the Employer of any part of the Works, except as may be specified in the Contract, - design of any part of the Works by the Employer's personnel or by others for whom the Employer is responsible, - any operation of the forces of nature affecting the Site and/or the Works, which was unforeseeable or against which an experienced contractor could not reasonably have been expected to take precautions, - Force Majeure, - a suspension under Sub-Clause 2.3 unless it is attributable to the contractor's failure, - any failure of the Employer, - physical obstructions or physical conditions, other than climatic conditions, encountered on the Site during the performance of the Works, which obstructions or conditions were not reasonably foreseeable by an experienced contractor and which the contractor immediately notified to the Employer, - any delay or disruption caused by any Variation, - any change to the law of the Contract after the date of the contractor's offer as stated in the Agreement, - losses arising out of the Employer's right to have the permanent work executed on, over, under, in or through any land, and to occupy this land for the permanent work, and - damage which is an unavoidable result of the contractor's obligations to execute the Works and to remedy any defects. |
| 7. Time for Completion |  |
| 7.1 Execution of the Works | The contractor shall commence the Works on the Commencement Date and shall proceed expeditiously and without delay and shall complete the Works within the Time for Completion. |
| 7.2 Programme | The contractor shall submit to the Employer a programme for the Works within the time stated in the Appendix. |
| 7.3 Extension of Time | Subject to Sub-Clause 10.3, the contractor shall be entitled to an extension to the Time for Completion if he is or will be delayed by any of the Employer's Liabilities. On receipt of an application from the contractor, the Employer shall consider all supporting details provided by the contractor and shall extend the Time for Completion as appropriate. |
| 7.4 Late Completion | If the contractor fails to complete the Works within the Time for Completion, the contractor's only liability to the Employer for such failure shall be to pay the amount stated in the Appendix for each day for which he fails to complete the Works. |

| 8. Taking-Over |  |
| --- | --- |
| 8.1 Completion | The contractor may notify the Employer when he considers that the Works are complete. |
| 8.2 Taking-Over Notice | The Employer shall notify the contractor when he considers that the contractor has completed the Works stating the date accordingly. Alternatively, the Employer may notify the contractor that the Works, although not fully complete, are ready for taking over, stating the date accordingly. The Employer shall take over the Works upon the issue of this notice. The contractor shall promptly complete any outstanding work and, subject to Clause 9, clear the Site. |
| 9. Remedying Defects |  |
| 9.1 Remedying Defects | The Employer may at any time prior to the expiry of the period stated in the Appendix, notify the contractor of any defects or outstanding work. The contractor shall remedy at no cost to the Employer any defects due to the contractor's design, materials, plant or workmanship not being in accordance with the Contract. The cost of remedying defects attributable to any other cause shall be valued as a Variation. Failure to remedy any defects or complete outstanding work within a reasonable time of the Employer's notice shall entitle the Employer to carry out all necessary work at the contractor's cost. |
| 9.2 Uncovering and Testing | The Employer may give instruction as to the uncovering and/or testing of any work. Unless as a result of any uncovering and/or testing it is established that the contractor's design, materials, plant or workmanship are not in accordance with the Contract, the Contractor shall be paid for such uncovering and/or testing as a Variation in accordance with Sub-Clause 10.2. |
| 10. Variations and Claims |  |
| 10.1 Right to Vary | The Employer may instruct Variations. |
| 10.2 Valuation of Variations | Variations shall be valued as follows: - At a lump sum price agreed between the Parties, or - where appropriate, at rates in the Contract, or - in the absence of appropriate rates, the rates in the Contract shall be used as the basis for valuation, or failing which - at appropriate new rates, as may be agreed or which the Employer considers appropriate, or - if the Employer so instructs, at daywork rates set out in the Appendix for which the contractor shall keep records of hours of labour and contractor's Equipment, and of Materials used. |
| 10.3 Early Warning | A Party shall notify the other as soon as he is aware of any circumstance which may delay or disrupt the Works, or which may give rise to a claim for additional payment. The contractor shall take all reasonable steps to minimise these effects. The contractor's entitlement to extension to the Time for Completion or additional payment shall be limited to the time and payment which would have been due if he had given prompt notice and has taken all reasonable steps. |
| 10.4 Right to Claim | If the contractor incurs cost as a result of any of the Employer's Liabilities, the contractor shall be entitled to the amount of such cost. If as a result of any of the Employer's Liabilities, it is necessary to change the Works, this shall be dealt with as a Variation. |
| 10.5 Variation and Claim Procedure | The contractor shall submit the Employer an itemised make-up of the value of Variations and claims within 28 days of the instruction or of the event giving rise to the claim. The Employer shall check and if possible agree the value. In the absence of agreement, the Employer shall determine the value. |
| 11. Contract Price and Payment |  |
| 11.1 Valuation of the Works | The Works shall be valued as provided for in the Appendix, subject to Clause 10. |
| 11.2 Monthly Statements | The contractor shall be entitled to be paid at monthly intervals: - the value of the Works executed, - the percentage stated in the Appendix of the value of Materials and Plant delivered to the Site at a reasonable time, subject to any additions or deductions which may be due. The contractor shall submit each month to the Employer a statement showing the amounts to which he considers himself entitled. |
| 11.3 Interim Payments | Within 28 days of delivery of each statement, the Employer shall pay to the contractor the amount shown in the contractor's statement less retention at the rate stated in the Appendix, and less any amount for which the Employer has specified his reasons for disagreement. The Employer shall not be bound by any sum previously considered by him to be due to the contractor. The Employer may withhold interim payments until he receives the performance security under Sub-Clause 4.4 (if any). |
| 11.4 Payment of First Half of Retention | One half of the retention shall be paid by the Employer to the contractor within 14 days after issuing the notice under Sub-Clause 8.2. |
| 11.5 Payment of Second Half of Retention | The remainder of the retention shall be paid by the Employer to the contractor within 14 days after either the expiry of the period stated in the Appendix, or the remedying of notified defects or the completion of outstanding work, all as referred to in Sub-Clause 9.1, whichever is the later. |
| 11.6 Final Payment | Within 42 days of the latest of the events listed in Sub-Clause 11.5 above, the contractor shall submit a final account to the Employer together with any documentation reasonably required to enable the Employer to ascertain the final contract value. Within 28 days after the submission of this final account, the Employer shall pay to the contractor any amount due. If the Employer disagrees with any part of the contractor's final account, he shall specify his reasons for disagreement when making payment |
| 11.7 Currency | Payment shall be in the currency stated in the Appendix. |
| 11.8 Delayed Payment | The contractor shall be entitled to interest at the rate stated in the Appendix for each day the Employer fails to pay beyond the prescribed payment period. |
| 12. Default |  |
| 12.1 Default by Contractor | If the contractor abandons the Works, refuses or fails to comply with a valid instruction of the Employer or fails to proceed expeditiously and without delay or is, despite a written complaint, in breach of the Contract, the Employer may give notice referring to this Sub-Clause and stating the default. If the contractor has not taken all practicable steps to remedy the default within 14 days after the contractor's receipt of the Employer's notice, the Employer may, by a second notice given within a further 21 days, terminate the Contract. The contractor shall then demobilise from the Site leaving behind Materials and Plant and any contractor's Equipment which the Employer instructs in the second notice is to be used until the completion of the Works. |
| 12.2 Default by Employer | If the Employer fails to pay in accordance with the Contract, or is, despite a written complaint, in breach of the Contract, the contractor may give notice referring to this Sub-Clause and stating the default. If the default is not remedied within 7 days after the Employer's receipt of this notice, the contractor may suspend the execution of all or parts of the Works. If the default is not remedied within 28 days after the Employer's receipt of the contractor's notice, the contractor may, by a second notice given within a further 21 days, terminate the Contract. The contractor shall then demobilise from the Site. |
| 12.3 Insolvency | If a Party is declared insolvent under any applicable law, the other Party may by notice terminate the Contract immediately. The contractor shall then demobilise from the Site leaving behind, in the case of the contractor's insolvency, any contractor's Equipment which the Employer instructs in the notice is to be used until the completion of the Works. |
| 12.4 Payment upon Termination | After termination, the contractor shall be entitled to payment of the unpaid balance of the value of the Works executed and of the Materials and Plant reasonably delivered to the Site, adjusted by the following: - any sums to which the contractor is entitled under Sub-Clause 10.4, - any sums to which the Employer is entitled, - if the Employer has terminated under Sub-Clause 12.1 or 12.3, the Employer shall be entitled to a sum equivalent to 20% of the value of those parts of the Works not executed at the date of the termination, - if the contractor has terminated under Sub-Clause 12.2 or 12.3, the contractor shall be entitled to the Cost of his suspension and demobilisation together with a sum equivalent to 10% of the value of those parts of the Works not executed at the date of termination The net balance due shall be paid or repaid within 28 days of the notice of termination. |
| 13. Risk and Responsibility |  |
| 13.1 Contractor's Care of the Works | The contractor shall take full responsibility for the care of the Works from the Commencement Date until the date of the Employer's notice under Sub-Clause 8.2. Responsibility shall then pass to the Employer. If any loss or damage happens to the Works during the above period, the contractor shall rectify such loss or damage so that the Works conform to the Contract. Unless the loss or damage happens as a result of an Employer's Liability, the contractor shall indemnify the Employer, the Employer's contractors, agents and employees against all loss or damage happening to the Works and against all claims or expense arising out of the Works caused by a breach of the Contract, by negligence or by other default of the contractor, his agents or employees. |
| 13.2 Force Majeure | If a Party is or will be prevented from performing any of its obligations by Force Majeure, the Party affected shall notify the other Party immediately. If necessary, the contractor shall suspend the execution of the Works and, to the extent agreed with the Employer, demobilise the contractor's Equipment. If the event continues for a period of 84 days, either Party may then give notice of termination which shall take effect 28 days after the giving of the notice. After termination, the contractor shall be entitled to payment of the unpaid balance of the value of the Works executed and of the Materials and Plant reasonably delivered to the Site, adjusted by the following: a. any sums to which the contractor is entitled under Sub-Clause 10.4, b. the Cost of his suspension and demobilisation, c. any sums to which the Employer is entitled. The net balance due shall be paid or repaid within 28 days of the notice of termination. |
| 14. Insurance |  |
| 14.1 Extent of Cover | The contractor shall, prior to commencing the Works, effect and thereafter maintain insurances in the joint names of the Parties: - for loss and damage to the Works, Materials, Plant and the contractor's Equipment, - for liability of both Parties for loss, damage, death or injury to third parties or their property arising out of the contractor's performance of the Contract, including the contractor's liability for damage to the Employer's property other than the Works, and - for liability of both Parties and of any Employer's representative for death or injury to the contractor's personnel except to the extent that liability arises from the negligence of the Employer, any Employer's representative or their employees. |
| 14.2 Arrangements | All insurances shall conform with any requirements detailed in the Appendix. The policies shall be issued by insurers and in terms approved by the Employer. The contractor shall provide the Employer with evidence that any required policy is in force and that the premiums have been paid. All payments received from insurers relating to loss or damage to the Works shall be held jointly by the Parties and used for the repair of the loss or damage or as compensation for loss or damage that is not to be repaired. |
| 14.3 Failure to Insure | If the contractor fails to effect or keep in force any of the insurances referred to in the previous Sub-Clauses, or fails to provide satisfactory evidence, policies or receipts, the Employer may, without prejudice to any other right or remedy, effect insurance for the cover relevant to such default and pay the premiums due and recover the same as a deduction from any other monies due to the contractor. |
| 15. Resolution of Disputes |  |
| 15.1 Adjudication | Unless settled amicably, any dispute or difference which arises between the contractor and the Employer out of or in connection with the Contract, including any valuation or other decision of the Employer, shall be referred by either Party to adjudication in accordance with the attached Rules for Adjudication ("the Rules"). The adjudicator shall be any person agreed by the Parties. In the event of disagreement, the adjudicator shall be appointed in accordance with the Rules. |
| 15.2 Notice of Dissatisfaction | If a Party is dissatisfied with the decision of the adjudicator or if no decision is given within the time set out in the Rules, the Party may give notice of dissatisfaction referring to this Sub-Clause within 28 days of receipt of the decision or the expiry of the time for the decision. If no notice of dissatisfaction is given within the specified time, the decision shall be final and binding on the Parties. If notice of dissatisfaction is given within the specified time, the decision shall be binding on the Parties who shall give effect to it without delay unless and until the decision of the adjudicator is revised by an arbitrator. |
| 15.3 Arbitration | A dispute which has been the subject of a notice of dissatisfaction shall be finally settled by a single arbitrator under the rules specified in the Appendix. In the absence of agreement, the arbitrator shall be designated by the appointing authority specified in the Appendix. Any hearing shall be held at the place specified in the Appendix and in the language referred to in Sub-Clause 1.5. |

Section V.	Particular Conditions

Notes on Particular Conditions It is intended that the Contract for Small Works will work satisfactorily without any Particular Conditions. However, if the requirement of the project makes it desirable to amend any Clause or to add provisions to the Contract, the amendments and additions should be set out on pages headed Particular Conditions. Care should be taken with the drafting of such Clauses especially in view of the high priority given to the Particular Conditions by Sub-Clause 1.3. Refer to Section XI Notes for Guidance for including additional clauses in Particular Conditions.

Add the following sub-clause after sub-clause 11.8:

| 11.9 Advance Payment | a The Employer shall make advance payment to the contractor of the amounts stated in the Appendix within 14 days, against provision by the contractor of an Unconditional Bank Guarantee in a form and by a bank acceptable to the Employer in amounts and currencies equal to the advance payment. The Guarantee shall remain effective until the advance payment has been repaid, but the amount of the Guarantee shall be progressively reduced by the amounts repaid by the contractor. Interest will not be charged on the advance payment. b The contractor is to use the advance payment only to pay for Equipment, Plant, Materials and mobilization expenses required specifically for execution of the Contract. The contractor shall demonstrate that advance payment has been used in this way by supplying copies of invoices or other documents to the Project Manager. c The advance payment shall be repaid by deducting proportionate amounts from payments otherwise due to the contractor, following the schedule of completed percentages of the Works on a payment basis. No account shall be taken of the advance payment or its repayment in assessing valuations of work done, variations, price adjustments, compensation events, bonuses or liquidated damages. |
| --- | --- |
| 11.10 Local Taxation & Value Added Tax | - The prices tendered by the Contractor shall include all taxes that may be levied in accordance to the laws and regulations in being in Nepal on the date 28 days prior to the closing date for submissions of Bids on the Contractor’s equipment, plant and materials acquired for the purpose of the Contract and on the services performed under the Contract. Nothing in the Contract shall relieve the Contractor from his responsibility to pay any tax that may be levied in Nepal on profits made by him in respect of the Contract. - The Contract is not exempted from value added tax. An amount specified in the schedule of taxes shall be paid by the Contractor in the concerned VAT office within time frame specified in VAT regulation. |

Section VI.	Forms of Securities

Notes on Forms of Securities Samples of acceptable forms of Bid, Performance, and Advance Payment Guarantees are annexed. Bidders should not complete the Performance and Advance Payment Guarantee forms at this time. Only the successful Bidder will be required to provide Performance and Advance Payment Guarantees in accordance with one of the forms or in a similar form acceptable to the Employer.

Bid Security (Bank Guarantee)

Whereas, [name of Bidder] (hereinafter called “the Bidder”) has submitted his bid dated [date] for the construction of [name of Contract] (hereinafter called “the bid”).

Know all people by these presents that We [name of Bank] of [name of country] having our registered office at [address] (hereinafter called “the Bank”) are bound unto [name of Employer] (hereinafter called “the Employer”) in the sum of [amount]1 for which payment well and truly to be made to the said Employer, the Bank binds itself, its successors, and assigns by these presents.

Sealed with the Common Seal of the said Bank this [day] day of [month], [year].

The conditions of this obligation are:

(1)	If, after bid opening, the Bidder withdraws his bid during the period of bid validity specified in the Form of Bid; or

(2)	If the Bidder having been notified of the acceptance of his bid by the Employer during the period of bid validity:

(a)	fails or refuses to execute the Form of Agreement in accordance with the Instructions to Bidders, if required; or

(b)	fails or refuses to furnish the Performance Security, in accordance with the Instruction to Bidders; or

(c)	does not accept the correction of the bid,

we undertake to pay to the Employer up to the above amount upon receipt of his first written demand, without the Employer’s having to substantiate his demand, provided that in his demand the Employer will note that the amount claimed by him is due to him owing to the occurrence of one or any of the three conditions, specifying the occurred condition or conditions.

This Guarantee will remain in force up to and including the date [number] days2 after the deadline for submission of bids as such deadline is stated in the Instructions to Bidders or as it may be extended by the Employer, notice of which extension(s) to the Bank is hereby waived. Any demand in respect of this Guarantee should reach the Bank not later than the above date.

Date 		Signature of the Bank ____________________________________

Witness 		Seal  ____________________________________

____________________________________________________________________________

[signature, name, and address]

## Performance Bank Guarantee

To:  [name and address of Employer]

Whereas [name and address of contractor] (hereinafter called “the contractor”) has undertaken, in pursuance of Contract No. [number] dated [date] to execute [name of Contract and brief description of Works] (hereinafter called “the Contract”);

And whereas it has been stipulated by you in the said Contract that the contractor shall furnish you with a Bank Guarantee by a recognized bank for the sum specified therein as security for compliance with his obligations in accordance with the Contract;

And whereas we have agreed to give the contractor such a Bank Guarantee;

Now therefore we hereby affirm that we are the Guarantor and responsible to you, on behalf of the contractor, up to a total of [amount of Guarantee] [amount in words]3 such sum being payable in the types and proportions of currencies in which the Contract Price is payable, and we undertake to pay you, upon your first written demand and without cavil or argument, any sum or sums within the limits of [amount of Guarantee]4 as aforesaid without your needing to prove or to show grounds or reasons for your demand for the sum specified therein.

We hereby waive the necessity of your demanding the said debt from the contractor before presenting us with the demand.

We further agree that no change or addition to or other modification of the terms of the Contract or of the Works to be performed there under or of any of the Contract documents which may be made between you and the contractor shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall be valid until a date 28 days from the date of issue of the Certificate of Completion.

Signature and seal of the Guarantor

Name of Bank

Address

Date

## Bank Guarantee for Advance Payment

To:	[name and address of Employer]

[name of Contract]

Gentlemen:

In accordance with the provisions of the Conditions of Contract, Clause 11.1 (“Advance Payment”) of the above-mentioned Contract, [name and address of contractor] (hereinafter called “the contractor”) shall deposit with [name of Employer] a Bank Guarantee to guarantee his proper and faithful performance under the said Clause of the Contract in an amount of [amount of Guarantee] [amount in words]5

We, the [Bank or Financial Institution], as instructed by the contractor, agree unconditionally and irrevocably to guarantee as primary obligator and not as Surety merely, the payment to [name of Employer] on his first demand without whatsoever right of objection on our part and without his first claim to the contractor, in the amount not exceeding [amount of Guarantee] [amount in words]6

We further agree that no change or addition to or other modification of the terms of the Contract or of Works to be performed there under or of any of the Contract documents which may be made between [name of Employer] and the contractor, shall in any way release us from any liability under this Guarantee, and we hereby waive notice of any such change, addition, or modification.

This Guarantee shall remain valid and in full effect from the date of the advance payment under the Contract until [name of Employer] receives full repayment of the same amount from the contractor.

Yours truly,

Signature and seal:

Name of Bank/Financial Institution:

Address:

Date:

Section VII.	Specification

Notes on the Specification A set of precise and clear specifications is a prerequisite for Bidders to respond realistically and competitively to the requirements of the Employer without qualifying or conditioning their bids. In the context of international competitive bidding, the specifications must be drafted to permit the widest possible competition and, at the same time, present a clear statement of the required standards of workmanship, materials, and performance of the goods and services to be procured. Only if this is done will the objectives of economy, efficiency, and fairness in procurement be realized, responsiveness of bids be ensured, and the subsequent task of bid evaluation facilitated. The specifications should require that all goods and materials to be incorporated in the Works be new, unused, of the most recent or current models, and incorporate all recent improvements in design and materials unless provided otherwise in the Contract. Samples of specifications from previous similar projects in the same country are useful in this respect. Most specifications are normally written specially by the Employer or Project Manager to suit the Contract Works in hand. There is no standard set of specifications for universal application in all sectors in all countries, but there are established principles and practices, which are reflected in these documents. There are considerable advantages in standardising General Specifications for repetitive Works in recognized public sectors, such as highways, ports, railways, urban housing, irrigation, and water supply, in the same country or region where similar conditions prevail. The General Specifications should cover all classes of workmanship, materials, and equipment commonly involved in construction, although not necessarily to be used in a particular Works Contract. Deletions or addenda should then adapt the General Specifications to the particular Works. Care must be taken in drafting specifications to ensure that they are not restrictive. In the specification of standards for goods, materials, and workmanship, recognized international standards should be used as much as possible. Where other particular standards are used, whether national standards of Nepal or other standards, the specifications should state that goods, materials, and workmanship that meet other authoritative standards, and which ensure substantially equal or higher quality than the standards mentioned, will also be acceptable. The following clause may be inserted in the Special Conditions or Specifications. Sample Clause: Equivalency of Standards and Codes Wherever reference is made in the Contract to specific standards and codes to be met by the goods and materials to be furnished, and work performed or tested, the provisions of the latest current edition or revision of the relevant standards and codes in effect shall apply, unless otherwise expressly stated in the Contract. Where such standards and codes are national, or relate to a particular country or region, other authoritative standards that ensure a substantially equal or higher quality than the standards and codes specified will be accepted subject to the Project Manager’s prior review and written consent. Differences between the standards specified and the proposed alternative standards shall be fully described in writing by the contractor and submitted to the Project Manager at least 28 days prior to the date when the contractor desires the Project Manager’s consent. In the event the Project Manager determines that such proposed deviations do not ensure substantially equal or higher quality, the contractor shall comply with the standards specified in the documents. These Notes for Preparing Specifications are intended only as information for the Employer or the person drafting the bidding documents. They should not be included in the final documents.

Section VIII.	Drawings

Notes on Drawings Insert here a list of Drawings. The actual Drawings, including site plans, should be attached to this section or annexed in a separate folder.

Section IX.	Bill of Quantities

Notes on Bill of Quantities Objectives The objectives of the Bill of Quantities are (a) to provide sufficient information on the quantities of Works to be performed to enable bids to be prepared efficiently and accurately; and (b) when a Contract has been entered into, to provide a priced Bill of Quantities for use in the periodic valuation of Works executed. In order to attain these objectives, Works should be itemised in the Bill of Quantities in sufficient detail to distinguish between the different classes of Works, or between Works of the same nature carried out in different locations or in other circumstances which may give rise to different considerations of cost. Consistent with these requirements, the layout and content of the Bill of Quantities should be as simple and brief as possible. Daywork Schedule A Daywork Schedule should be included only if the probability of unforeseen work, outside the items included in the Bill of Quantities, is high. To facilitate checking by the Employer of the realism of rates quoted by the Bidders, the Daywork Schedule should normally comprise the following: (a) A list of the various classes of labour, materials, and Construction Equipment for which basic daywork rates or prices are to be inserted by the Bidder, together with a statement of the conditions under which the contractor will be paid for work executed on a daywork basis. (b) Nominal quantities for each item of Daywork, to be priced by each Bidder at Daywork rates as bid. The rate to be entered by the Bidder against each basic Daywork item should include the contractor’s profit, overheads, supervision, and other charges. Provisional Sums A general provision for physical contingencies (quantity overruns) may be made by including a provisional sum in the Summary Bill of Quantities. Similarly, a contingency allowance for possible price increases should be provided as a provisional sum in the Summary Bill of Quantities. The inclusion of such provisional sums often facilitates budgetary approval by avoiding the need to request periodic supplementary approvals as the future need arises. Where such provisional sums or contingency allowances are used, the Appendix should state the manner in which they will be used, and under whose authority (usually the Project Manager’s). These Notes for Preparing a Bill of Quantities are intended only as information for the Employer or the person drafting the bidding documents. They should not be included in the final documents.

Section X.	Rules for Adjudication

| Referred to in Sub-Clause 15.1 |  |
| --- | --- |
| General | 1. Any reference in the Conditions of Contract to the Rules for Adjudication shall be deemed to be a reference to these Rules. 2. Definitions in the Contract shall apply in these Rules. |
| Appointment of Adjudicator | 3. The Parties shall jointly ensure the appointment of the Adjudicator. The Adjudicator shall be a suitably qualified person. 4. If for any reason the appointment of the Adjudicator is not agreed at the latest within 14 days of the reference of a dispute in accordance with these Rules, then either Party may apply, with a copy of the application to the other Party, to any appointing authority named in the Contract or, if none, to the President of Nepal Council of Arbitration (NEPCA) or his nominee, to appoint an Adjudicator, and such appointment shall be final and conclusive. 5. The Adjudicator's appointment may be terminated by mutual agreement of the Parties. The Adjudicator's appointment shall expire when the Works have been completed or when any disputes referred to the Adjudicator shall have been withdrawn or decided, whichever is the later. |
| Terms of Appointment | 6. The Adjudicator is to be, and is to remain throughout his appointment, impartial and independent of the Parties and shall immediately disclose in writing to the Parties anything of which he becomes aware which could affect his impartiality or independence. 7. The Adjudicator shall not give advice to the Parties or their representatives concerning the conduct of the project of which the Works form part other than in accordance with these Rules. 8. The Adjudicator shall not be called as a witness by the Parties to give evidence concerning any dispute in connection with, or arising out of, the Contract. 9. The Adjudicator shall treat the details of the Contract and all activities and hearings of the Adjudicator as confidential and shall not disclose the same without the prior written consent of the Parties. The Adjudicator shall not, without the consent of the Parties, assign or delegate any of his work under these Rules or engage legal or technical assistance. 10. The Adjudicator may resign by giving 28 days' notice to the Parties. In the event of resignation, death or incapacity, termination or a failure or refusal to perform the duties of Adjudicator under these Rules, the Parties shall agree upon a replacement Adjudicator within 14 days or Rule 4 shall apply. 11. The Adjudicator shall in no circumstances be liable for any claims for anything done or omitted in the discharge of the Adjudicator's duties unless the act or omission is shown to have been in bad faith. 12. If the Adjudicator shall knowingly breach any of the provisions of Rule 6 or act in bad faith, he shall not be entitled to any fees or expenses hereunder and shall reimburse each of the Parties for any fees and expenses properly paid to him if, as a consequence of such breach any proceedings or decisions of the Adjudicator are rendered void or ineffective. |
| Payment | 13. The Adjudicator shall be paid the fees and expenses set out in the Adjudicator's Agreement. 14. The retainer fee, if applicable, shall be payment in full for: (a) being available, on 28 days' notice, for all hearings and Site visits; (b) all office overhead expenses such as secretarial services, photocopying and office supplies incurred in connection with his duties; (c) all services performed hereunder except those performed during the days referred to in Rule 15. 15 The daily fee shall be payable for each working day preparing for or attending Site visits or hearings or preparing decisions including any associated travelling time. 16. The retainer and daily fees shall remain fixed for the period of tenure of the Adjudicator. 17. All payments to the Adjudicator shall be made by the contractor who will be entitled to be reimbursed half by the Employer. The contractor shall pay invoices addressed to him within 28 days of receipt. The Adjudicator's invoices for any monthly retainer shall be submitted quarterly in advance and invoices for daily fees and expenses shall be submitted following the conclusion of a Site visit or hearing. All invoices shall contain a brief description of the activities performed during the relevant period. The Adjudicator may suspend work if any invoice remains unpaid at the expiry of the period for payment, provided that 7 days prior notice has been given to both Parties. 18. If the contractor fails to pay an invoice addressed to it, the Employer shall be entitled to pay the sum due to the Adjudicator and recover the sum paid from the contractor. |
| Procedure for Obtaining Adjudicator's Decision | 19. A dispute between the Parties may be referred in writing by either Party to the Adjudicator for his decision, with a copy to the other Party. If the Adjudicator has not been agreed or appointed, the dispute shall be referred in writing to the other Party, together with a proposal for the appointment of an Adjudicator. A reference shall identify the dispute and refer to these Rules. 20. The Adjudicator may decide to visit the Site. The Adjudicator may decide to conduct a hearing in which event he shall decide on the date, place and duration for the hearing. The Adjudicator may request that written statements from the Parties be presented to him prior to, at or after the hearing. The Parties shall promptly provide the Adjudicator with sufficient copies of any documentation and information relevant to the Contract that he may request. 21. The Adjudicator shall act as an impartial expert, not as an arbitrator, and shall have full authority to conduct any hearing as he thinks fit, not being bound by any rules or procedures other than those set out herein. Without limiting the foregoing, the Adjudicator shall have power to: (a) decide upon the Adjudicator's own jurisdiction, and as to the scope of any dispute referred to him, (b) make use of his own specialist knowledge, if any, (c) adopt an inquisitorial procedure, - decide upon the payment of interest in accordance with the Contract, - open up, review and revise any opinion, instruction, determination, certificate or valuation, related to the dispute, - refuse admission to hearings to any persons other than the Employer, the contractor and their respective representatives, and to proceed in the absence of any Party who the Adjudicator is satisfied received notice of the hearing. 22. All communications between either of the Parties and the Adjudicator and all hearings shall be in the language of the Adjudicator's Agreement. All such communications shall be copied to the other Party. 23. No later than the fifty-sixth day after the day on which the Adjudicator received a reference or, if later, the day on which the Adjudicator's Agreement came into effect, the Adjudicator shall give written notice of his decision to the Parties. Such decision shall include reasons and state that it is given under these Rules. |

Adjudicator's Agreement

Identification of Project:

(the "Project")

Name and address of the Employer:

(the "Employer")

Name and address of contractor:

(the "contractor")

Name and address of Adjudicator:

(the "Adjudicator")

Whereas the Employer and the contractor have entered into a contract ("the Contract") for the execution of the Project and wish to appoint the Adjudicator to act as adjudicator in accordance with the Rules for Adjudication ["the Rules"].

The Employer, Contractor and Adjudicator agree as follows:

- The Rules and the dispute provisions of the Contract shall form part of this Agreement.

- The Adjudicator shall be paid:

A retainer fee of ________________________________________ per calendar month

(where applicable)

A daily fee of __________________________________________

Expenses (including the cost of telephone calls, courier charges, faxes and telexes incurred in connection with his duties; all reasonable and necessary travel expenses, hotel accommodation and subsistence and other direct travel expenses).

Receipts will be required for all expenses.

- The Adjudicator agrees to act as adjudicator in accordance with the Rules and has disclosed to the Parties any previous or existing relationship with the Parties or others concerned with the Project.

- This Agreement shall be governed by the law of Nepal.

- The language of this Agreement shall be English [or in Nepali if both parties agrees].

SIGNED BY _________________________________________

for and on behalf of the Employer in the presence of

Witness	___________________________________________

Name	___________________________________________

Address	___________________________________________

Date	___________________________________________

SIGNED BY ________________________________________

for and on behalf of the contractor in the presence of

Witness	___________________________________________

Name	___________________________________________

Address	___________________________________________

Date	___________________________________________

SIGNED BY ________________________________________

for and on behalf of the Adjudicator in the presence of

Witness	___________________________________________

Name	___________________________________________

Address	___________________________________________

Date	___________________________________________

Section XI.	Notes for Guidance

(Not forming part of the Contract)

| General | The objective of this Contract is to express in clear and simple terms traditional procurement concepts. The Contract is intended to be suitable for works of simple content and short duration. If it is required that the contractor should undertake design, this is also provided for. There are no Particular Conditions, although these Notes contain alternative wording for consideration in particular circumstances. All necessary additional information is intended to be provided in the Appendix. A single document is proposed for the form of tender and the agreement. This reflects the simple projects envisaged. One result of the simple form of Contract is that there is an increased burden on the Employer to set out in the Specification and Drawings the full scope of works, including the extent of any design to be done by the contractor. There is no Engineer or Employer's Representative in the formal sense used in some other FIDIC Conditions. The Employer takes all necessary actions. However, the Employer must nominate his authorised spokesman and, if he wishes to engage a consultant to administer the Contract, may appoint a representative with specific delegated duties and authority. The contractor also nominates a representative. The Conditions contain no overall limit on the contractor's liability. If such a limit is required, a Clause should be inserted in the Particular Conditions. |  |
| --- | --- | --- |
| Agreement | When the applicable law imposes any form of tax such as VAT on the Works, the Employer should make clear whether tenderers should include such taxes in their prices. Similarly, if payment is to be made in whole or in part in a currency other than the currency of the Country, the Employer should make this clear to tenderers. See Sub-Clause 11.7. |  |
| Appendix | Any Notes for Guidance on the completion of the Appendix are to be found in the Notes to the Clauses concerned. The Employer should complete the Appendix as indicated prior to inviting tenders. Tenderers may be asked to insert a Time for Completion at 1.1.12 if none is specified. Where tenderers are required to submit design with their tenders, the documents containing the tendered design should be identified by the tenderer against item 1.1.1(f) of the Appendix. A number of suggestions have been made in the Appendix, such as the time for submission of the contractor's programme under Sub-Clause 7.2 and the amount of retention under Sub-Clause 11.4. If these suggestions are adopted by the Employer, no action is required. Otherwise, they should be deleted and replaced. |  |
| General Provisions | 1.1 Definitions. The definitions in these Conditions are not all the same as those to be found in other FIDIC Contracts. This is as a result of the need for simplicity in Conditions of this sort. Significantly different definitions include Commencement Date, Site, Variation and Works. 1.1.1 "Contract". The list of documents serves two purposes: firstly, to identify which documents form part of the Contract; and secondly, to provide an order of priority in the event of conflict between them. Document identification is necessary to avoid any possible doubt, for example because specifications have been subject to revisions. A complete list of Drawings is always desirable and could be attached on a separate sheet. There is no need for Particular Conditions but if amendments to these Conditions are required, they should be inserted on the sheet headed Particular Conditions and given priority over the General Conditions. If none, delete the reference. The Specification should set out in clear terms any design that the contractor is required to undertake, including the extent to which any design proposals are to be submitted with the tender. If none, the reference to the contractor's tendered design should be deleted. If there is no bill of quantities, delete the reference. If there are additional documents which are required to form part of the Contract, such as schedules of information provided by the contractor, these should be added by the Employer. Consideration should be given in each case to the required priority. If a letter of acceptance is used, it should be given high priority, with or in place of the Agreement, for example. 1.1.10 "Commencement Date". The starting date for the Contract is 14 days after the date when the contractor signs the Agreement with the Employer, unless the Parties agree otherwise. 1.1.19 "Force Majeure" may include, but is not limited to, exceptional events or circumstances of the kind listed below, so long as all of the five conditions stated in the definition have been satisfied: a) war, hostilities (whether war be declared or not), invasion, act of foreign enemies, b) rebellion, terrorism, revolution, insurrection, military or usurped power, or civil war, c) riot, commotion, disorder, strike or lockout by persons other than the contractor's personnel and other employees, d) munitions of war, explosive materials, ionising radiation or contamination by radioactivity, except as may be attributable to the contractor's use of such munitions, explosives, radiation or radioactivity, and e) natural catastrophes such as earthquake, hurricane, typhoon or volcanic activity. 1.1.24 "Works". The term "Works" is intended to cover all the obligations of the contractor, including any design and the remedying of defects. 1.5 Communications. The problem of languages is addressed by requiring the important communications such as notices and instructions to be in the language stated in the Appendix. Otherwise there is no "Ruling Language". Any arbitration will be conducted in the specified language. 1.6 Changes to the law after the date of the contractor's offer are at the Employer's risk and any delay or additional cost are recoverable by the contractor. If the law of the Contract is not the law of the Country, then Sub-Clause 1.4 should be changed in the Particular Conditions. |  |
| The Employer | 2.1 Unless the Parties have agreed otherwise, the Site must be handed over by the Employer to the contractor on the Commencement Date. This is 14 days after the Contract has come into effect, which occurs when the signed Agreement has been returned by the Employer to the contractor. 2.2 If for any reason, permits etc may also be required from places other than the Country, this Sub-Clause could be limited by the addition at the end of the words: "... in the Country but not elsewhere." 2.4 The term "approval" is only used in the Conditions in relation to the performance security at Sub-Clause 4.4 and insurances at Sub-Clause 14.1. It is important that risks such as those of poor workmanship or contractor's design are not transferred to the Employer unintentionally. The Sub-Clause is intended to prevent argument. |  |
| Employer's Representatives | 3 Two principles guided the drafting of this Clause. Firstly, the contractor should know who in an Employer Organisation is authorised to speak and act for the Employer at any given time. This is achieved by Sub-Clause 3.l: the authorised individual should be named in the Appendix. Secondly, those Employers who require professional assistance should not be discouraged from doing so and their consultant should have clearly established delegated powers. This is the object of Sub-Clause 3.2. Once appointed, the Employer's representative acts for and in the interests of the Employer. There is no dual role or duty to be impartial. If an impartial Employer's Representative is required with a role similar to the traditional Engineer, then the following words could be used in the Particular Conditions: "Replace the final sentence of Sub-Clause 3.2 with the following: "The Employer's Representative shall exercise in a fair and impartial manner the powers of the Employer under or in connection with the following Sub-Clauses: 1.3, 2.3, 4.2, 4.3, 5.1, 7.3, 8.2, 9.1, 9.2, 10.1, 10.2, 10.5, 11.1 to 11.6, 11.8, 12.1, 13.2 and 14. 1." To the extent that the Employer has delegated powers to an Employer's representative, he should be careful not to exercise such powers himself in order to avoid the risk of conflicting instructions, decisions etc. |  |
| The Contractor | 4.1 Most contracts do not specify the exact standard required for each element of the Works, so some benchmark standard is needed with which the contractor is to comply. If a more specific set of standards could be referred to for a particular project, then an amendment in the Particular Conditions would be desirable. 4.4 Performance Security. Suggested forms of performance bond (surety bond) or bank guarantee have not been provided. If it is felt that the scale of project warrants security by means of a bond, then local commercial practice should dictate the form. Example forms are included with FIDIC's Conditions of Contract for Construction. The amount and a reference to the desired form of any required security should be set out in the Appendix. |  |
| Design by Contractor | 5.1 As with all design-build contracts it is essential that the Employer's requirements are set out clearly and precisely. The Appendix should indicate to tenderers the Sub-Clause(s) in the Specification that set out the design requirement. Where the Employer procures any part of the design, the responsibility for design will be shared as this Contract makes the contractor responsible only for design prepared by him. The extent of the contractor's design obligation should therefore be clearly stated if disputes are to be avoided. The Conditions avoid the confusing concept of approval of design. Designs are submitted and may be returned with comments or rejected. The Employer need not react at all. 5.2 The contractor's responsibility for his design remains, as is made clear here and in Sub-Clause 2.4. In the event of conflict between the Specification and Drawings and the contractor's tendered design, the order of priority in the Appendix makes it clear that the Employer's documents prevail. This means that if the Employer prefers the contractor's tendered solution, the Specification and Drawings should be amended before the Contract is signed by the Parties. The contractor will have an absolute obligation to ensure that the parts of the Works designed by him are fit for their purpose, provided that the intended purposes are defined in the Contract. The Employer must therefore make clear in the parts of the Specification that impose design obligations, the intended purposes of the part of the Works to be designed by the contractor. This should be done even where this seems obvious in order to avoid argument about whether an intended purpose is defined or not. If a party wishes to protect the intellectual property in his design, provision must be made in the Particular Conditions. |  |
| Employer's Liabilities | 6.1 This Sub-Clause gathers together in one place the grounds for extension of time under Sub-Clause 7.3 and the grounds for claims under Sub-Clause 10.4. There is no time or claim for bad weather although this could be adjusted in the Particular Conditions if so required. |  |
| Time for Completion | 7.2 The Appendix should stipulate any particular requirements as to the form and level of detail of programme to be submitted. Where contractor's design is required, the Appendix could stipulate that the programme should show the dates on which it is intended to prepare and submit drawings etc. 7.3 The test for entitlement to an extension of time is whether it is appropriate. This means that if an event under Sub-Clause 6.1 caused critical delay to the Works and it is fair and reasonable to grant an extension of time, the Employer should do so. An extension of time should not be granted to the extent that any failure by the contractor to give an early warning notice under Sub-Clause 10.3 contributed to the delay. 7.4 There is a maximum amount which the contractor is liable to pay for late completion specified in the Appendix. 10% of the sum stated in the Agreement is suggested. |  |
| Taking-Over | 8.2 In line with normal practice, it is not envisaged that the Works need be 100% complete before the Employer may take over. Once the Works are ready to be used for their intended purpose, the notice should be given. There is no provision for taking-over of only parts of the Works but if this is required, provision should be made in the Particular Conditions. If any tests are required to be completed prior to taking-over, these should be specified in the Specification. The definition of Works is broad enough to include any such tests. |  |
| Remedying Defects | 9.1 There is no defined Defects Liability Period but during the period - normally 12 months - from the date of taking-over, the Employer may notify the contractor of defects. The contractor must remedy such defects within a reasonable time. If he fails to do so, the Employer may employ others for that purpose at the contractor's cost. The Employer may also notify defects at any time prior to taking-over. The liability of the contractor for defects will not normally end with the expiry of the period stated in the Appendix. Although he is then no longer obliged to return to Site to remedy defects, the defect represents a breach of contract for which the contractor is liable in damages. This liability remains for as long as the law of the Contract stipulates, often 3, 6 or 10 years from the date of the breach. If this long-term liability is to be reduced or eliminated, a Clause in the Particular Conditions is required. |  |
| Variations and Claims | 10.1 Variation is defined to include any change to the Specification or Drawings included in the Contract. If the Employer requires a change to part of the Works designed by the contractor either as part of his tender or after the Contract was awarded, then this is to be done by way of an addition to the Specification or Drawings which by Sub-Clause 5.2 will prevail over contractor's design. 10.2 This Sub-Clause sets out alternative procedures for the valuation of Variations, to be applied in the order of priority given. It applies equally to omissions as to additional works. - A lump sum should be the first method to be considered as it can encompass the true cost of a Variation and avoid subsequent dispute over the indirect effect. The Employer can invite the contractor to submit an itemised make-up (Sub-Clause 10.5) before instructing the Variation so that an agreed lump sum can form part of the instruction. b) Alternatively, a more traditional approach can be taken by valuing the Variation at rates in the bill of quantities and any schedules, or - using these rates as a basis, or - using new rates. e) Daywork rates are normally used when the Variation is of an indeterminate nature or is out of sequence with the remaining Works. To ensure reasonable daywork rates, provision should be made for these to be priced competitively in the tender documents. 10.3 This Sub-Clause and Sub-Clause 10.5 require the contractor to notify the Employer of events promptly and to detail any claim within 28 days. If the effects of the event are increased or if the ability of the Employer to verify any claim is affected by the failure to notify, then the Employer is protected. |  |
| Contract Price and Payment | 11.1 Normally only one of the options in the Appendix should be used to indicate how the sum in the offer is be calculated and presented. The following explains what is intended: |  |
|  | Lump sum price | A lump sum offer without any supporting details. This would be used for very minor works where Variations are not anticipated and the Works will be completed in a short period requiring only one payment to the contractor |
|  | Lump sum price with schedule of rates | A lump sum offer supported by schedules of rates prepared by the tenderer. This would be a larger contract where Variations and stage payments would be required. If the Employer does not have the resources to prepare his own bill of quantities then this alternative would be suitable. |
|  | Lump sum price with bill of quantities | A lump sum offer based on bill of quantities prepared by the Employer. This would be the same as last but where the Employer has the resources to prepare his own bill of quantities. A better contract would result with an Employer's bill of quantities. |
|  | Remeasurement with bill of quantities | A sum subject to remeasurement at the rates offered by the tenderer in the bill of quantities prepared by the Employer. This would be the same as last but would suit a contract where many changes are envisaged to the Works after the Contract has been awarded. |
|  | Cost reimbursable | An estimate prepared by the tenderer which will be replaced by the actual cost of the Works calculated in accordance with the terms set by the Employer. This would suit a project where the extent of work cannot be ascertained before the Contract is placed. An example of this would be an emergency reconstruction of a building damaged by fire. |
|  | However, if for some special reason, more than one option is selected, for example there is a remeasureable element in a lump sum Contract, then the details should be carefully defined. This Standard Bidding Document is intended for works of short duration. In the event of a contract for works of long duration, a new clause could be inserted at Sub-Clause 11. 1 to adjust for the rise and fall in the cost of labour, materials and other imports to the Works. Such a clause could be adapted from the other FIDIC Conditions of Contract. |  |
|  | 11.2 If the Contract is for a lump sum, consideration should be given as to how the work is to be valued for the purposes of interim payments. In completing the Appendix for Sub-Clause 11.1, the Employer may request Bidders to submit a cash flow forecast linked to a stage payment proposal for agreement. This would be reviewed in the event of an extension of time made in accordance with Sub-Clause 7.3. Alternatively, interim payment can be based on valuation of the Works which would also be appropriate for remeasurement and cost reimbursable Contracts. Payment could also be based on the achievement of milestones or a schedule of activities to which values are assigned. If local law or practice so dictates, an invoice may also be required, in which case it could be submitted with the statement. 11.3 No provision is made for advance payments. If such a payment is to be made, there should be provision in the Particular Conditions and for any security to be provided by the contractor. An example form of advance payment guarantee is to be found in FIDIC's Conditions of Contract for Construction. 11.4 The deduction of retention is sometimes replaced by the provision of security by the contractor to the Employer. Alternatively, the entire retention sum deducted is released after taking-over upon the provision by the contractor of security. In either event, suitable text would be required in the Particular Conditions. An example form of retention guarantee is to be found in FIDIC's Conditions of Contract for Construction. 11.5 The release of the second part of the retention will serve as confirmation that all notified defects have been remedied. 11.7 It is assumed that payments will be in a single currency. If this is not the case, the proportions of different currencies should be stated in the Appendix and provision made in the Specification or the Particular Conditions as to how payment is to be made. |  |
| Default | 12.1 The Employer may terminate the Contract if the defaulting contractor does not respond to a formal notice by taking all practicable steps to put right his default. This recognises that not all defaults are capable of correction in 14 days. If termination takes place, the Employer may take over and use the contractor's Equipment to complete the Works. Care should be taken, however, if the equipment on Site is hired: no specific provision is made to cover this situation and the Employer is unlikely to be able to retain such equipment. 12.2 This provision provides the contractor's main remedy for non-payment. 7 days after the Employer's receipt of a default notice, which must refer to Sub-Clause 12.2, the contractor may suspend all or part of his work. 21 days later the option to terminate arises if the Employer persists with non-payment or other default. The contractor must use his right to terminate within 21 days or lose it. This is to prevent a party abusing a right to terminate in his dealings with the other party for the remainder of the project. If contractor's Equipment is essential for the safety or stability of the Works, the Employer will be obliged to agree terms with the contractor for the retention of such equipment. Local law will often protect the Employer from the immediate and reckless removal of essential items. 12.3 The right of the Employer to retain the contractor's Equipment may clash with the right of a liquidator or receiver to realise the assets of an insolvent contractor. Reference to the applicable law would be necessary. 12.4 This Sub-Clause enables the financial aspects of the Contract to be resolved quickly and without the necessity to await the completion of the Works by others. By specifying the damages payable to the innocent party for the defaults leading to the termination, much delay, complication and scope for dispute are avoided. The Employer's costs in obtaining a replacement contractor will generally be higher than the contractor's loss of profit. |  |
| Risk and Responsibility | 13.1 Although the contractor is responsible for the Works prior to taking-over, he is protected by the obligation to insure the Works under Clause 14 and by his ability to recover under Clause 6 his Cost if one of the Employer's Liabilities occurs. 13.2 To qualify as Force Majeure, events must prevent performance of an obligation. See also the definition at Sub-Clause 1.1.19. Notice must be given at once. |  |
| Insurance | 14.1 The Employer should set out his precise requirements in the Appendix. Third Party, public liability insurance would normally be mandatory. As smaller contracts are likely to fall within tenderers' standing contractors' All Risk (CAR) insurance policies, tenderers should generally be asked to submit details of their insurance cover with their tenders. Any requirements for insurance after the date of the Employer's notice under Sub-Clause 8.2, or arising from taking-over parts of the Works, should be covered by Particular Conditions. See also Clause 13. If the Employer wishes to take out the insurances instead of the contractor, the following should be used as a Particular Condition in place of Sub-Clause 14.1: "Replace the text of Sub-Clause 14.1 with the following: "The Employer shall, prior to the Commencement Date, effect insurance in the joint names of the Parties of the types, in the amounts and with the exclusions stipulated in the Appendix. The Employer shall provide the contractor with evidence that any required policy is in force and that the premiums have been paid." Sub-Clauses 14.2 and 14.3 should be deleted if the Employer takes out the insurances. It should be noted that in the event of the Employer's failure to insure, the contractor may give notice under Sub-Clause 12.2. |  |
| Resolution of Disputes | 15.1 There are advantages in appointing an adjudicator from the outset even though the adjudicator may not be required to take any action or earn any fee unless and until a dispute is referred to him. Delays will inevitably occur if the-parties initiate the procedure to appoint an adjudicator only when a dispute has arisen. It is therefore recommended that the Employer propose a person to act as adjudicator either at tender stage or shortly after the Agreement is signed and that the matter is discussed and agreed as soon as possible. Care should be taken about whether an adjudicator should be local or from a neutral country. Although the adjudicator should be impartial, the costs of employing someone from a third country could be disproportionate if it is necessary for the adjudicator to visit or if a hearing became necessary. However, in view of the costs involved in arbitration, even of minor disputes, any extra cost of a truly impartial adjudicator is a recommended investment. It is intended that all decisions made by the Employer or his representative should be capable of being reviewed by an adjudicator and, if required, by an arbitrator. 15.3 Arbitration may not be commenced unless the dispute has first been the subject of an adjudication. The Rules of arbitration should be stipulated in the Appendix. The NEPCA Rules are recommended. The place of arbitration is significant as the arbitration law of the place of arbitration will apply in such matters as the ability of a party to appeal. |  |

Federation Internationale des Ingenieurs-Conseils, International Federation of Consulting Engineers.

Qualification is required only if the contract cost estimate is over Rs. 10 million.  If qualification is not required replace text with "None".

This amount is usually not less than 1.5 times the estimated annual cash flow for the Contract.

Usually the equivalent of the estimated payments flow over 4-6 months at the average (straight line distribution) construction rate.  The actual period of reference will depend on the speed with which the Employer will pay the Contractor’s monthly certificates.

If no qualification required, delete items for clauses 4(a), 4(c) and 4(e).

Delete “corrected and” or “and modified” if not applicable.  See Notes on Standard Form of Agreement, next page.

* Employer to specify as appropriate

1	 	The Bidder should insert the amount of the Guarantee in words and figures denominated in Nepali Rupees.  This figure should be the same as shown in Clause 13 of the Instructions to Bidders.

2	 	Usually 28 days after the end of the validity period of the bid.  The date should be inserted by the Employer before the bidding documents are issued.

3	 	An amount is to be inserted by the Guarantor, representing the percentage of the Contract Price specified in the Contract, and denominated in Nepalese Rupees.

4	 	The Unconditional (or “On-Demand”) Bank Guarantee has the merit of simplicity and of being universally known and accepted by commercial banks.  The contracting community, however, strongly objects to this type of Security because the Guarantee can be called (or threatened to be called) by Employers without justification.  Employers should recognize the contractual conditions governing nonperformance by the Contractor and should normally act only on the advice of the Project Manager in calling a Performance Guarantee.

5	 	An amount is to be inserted by the Bank or Financial Institution representing the amount of the Advance Payment, and denominated in Nepali Rupees of the Advance Payment as specified in the Contract.

6	 	An amount is to be inserted by the Bank or Financial Institution representing the amount of the Advance Payment, and denominated in Nepali Rupees.