## LTG Website text amendments
LTG pages that need amendment
| Page - content only | progress | Submitted | completed |  | Page - Layout only | progress | Submitted | completed
1 | About Us | 1st Draft complete | 11/05/2020 |  | 1 | About Us | Started
2 | Categories Page |  |  |  | 2 | Privacy Policy
3 | Commercial Ad space request |  |  |  | 3 | T&Cs for website
4 | Contact Us Page | 1st Draft complete | 11/05/2020 | 30/062020 | 4 | Safe Trade Zone reg page
5 | How does our site work page | 1st Draft complete | 11/05/2020 | 30/062020 | 5 | Commercial Ad space request | Started
6 | Organization Exchange | Updated. | 15/05/2020 | 30/062020 | 6 | T & Cs page for advertisers
7 | Privacy Policy | 1st Draft complete | 11/05/2020 | 30/062020 | 7 | Contact Us Page | Started
8 | Safe Trade Zobe reg page | Updated. | 15/05/2020 | 30/062020 | 8 | Home page
9 | T & Cs page for advertisers | Updated. | 15/05/2020 | 30/062020 | 9 | Categories Page
10 | T&Cs for website | 1st Draft complete | 11/05/2020 |  | 10 | How it work page
11 | Covid 19 Info page | 1st Draft complete | 11/05/2020 |  | 11 | Organization Exchange
[5 empty] | 12 | Login Page | Started
[5 empty] | 13 | Register Acc - individual
| LTG To do list | Progress | submitted | Completed | 14 | Register Acc - Organisation
1 | Get email back | Completed | 13/05/2020 | completed | 15 | Post a Listing
2 | Get access to backend | Awaiting feedbacak frorrm developers |  | completed
3 | Finalise research | In progress
4 | Update content | In progress
5 | Work on layout. | In progress
6 | research implication of trading alcohol during lock down | In progress |  | Completed
7 | Update SSL certificate of website | Stu & Afrihost | 13/05/2020 | Completed
8 | Infographics content update
9 | Mascot Speech Bubbles | Started
10 | Email content to traders

## LTG Layout amendments
LTG Developers timeline
| Completed | reviewed | corrections | complete
1. New UI/UX Design creation and implementation (20 days)
2. Remove Parental approval feature (2 days)
3. Register feature modifications on the age limits (1 day)
4. Modification on subscriber email template (2 days)
5. User Roles can be modified/categorized to manage proper workflow (1 day)
6. Mascots are to be removed or changed to be suitable with modified conditions. (2 days)
7. During Product creation and Deal finalization, the notification to parents should be removed. (2 days)
8. Questions during Rating can be modified. (1 day)
9. Commercial Ad Space requests can include monetary terms and conditions. (4 days)
10. Category names can be modified. (1 day)
11. Voucher implementation with card payment integrations. (10 days)
12. Filtration of message chats as per the product listings. (4 days)
13. Trade process modification may be via Phone call as well. (4 days)
14. After login, Dashboard can be modified to show some data visualization and latest updated data lists. (4 days)
15. Buffer time, Testing, security (10 days)

## Corrections
Corrections needed for website LTG
1 | Add Covid-19 Info Article | Add to Home page by Trade Zone map. |  | Screenshot uploaded to Dropbox.
2 | Administrator Settings
Site administrator to be changed to rothea@letstradegoods.co.za
|  | Admin Emails | Trade Zone Register | - a request needs to come to the Site admin (needs to be notified via email)
|  |  | Contact Us | - a request needs to come to the Site admin (needs to be notified via email)
|  |  | Reporting of a listing/user | - a request needs to come to the Site admin (needs to be notified via email)
|  |  | Commercial Ad request | - a request needs to come to the Site admin (needs to be notified via email)
|  |  | Low rated users | Site admin needs to be notified if a user is rated low.
|  |  | Flagged Words | words on the flagged list, when used needs to be reported to site admin.
3 | Registering of a Childs profile | Parental Approval needed
Parent needs to be able to remove listing if need be.
Parent ID, address and email adress shows an error when registering a childs account.
4 | Trade Finalization email | Add link to the trade.
5 | Safe Trade Zone | Remove the word Safe from Safe Trade Zone throughout website.
Allow all organisation types to function as Trade Zones and appear on map during the phase of finalising the deal.
Registering error, address appears with Trade Location name should be.
6 | Remove the category | Livestock + Live animals
7 | Mascot Speech Bubbles | Font size needs to be bigger.
Screenshots are loaded to dropbox of the text corrections needed.
8 | During trading | When user selects Trade Zone, there is an error on the calender where date of trade need to be added.(Screenshot loaded to Dropbox)
9 | Category & Favourites list | Once item is traded off,(By other traders) item needs to be removed from other trader's lists and website if trade was successful
10 | Traders need to edit TZ location | Once deal is finalised with the selected Trade Zone, traders cannot edit the Trade Zone Location, only time and Date. Users need to be able to edit location as well.
11 | Churches | Churches need to be added to Trade Zone map like schools
Churches need to be added as an organisation type during registration.
Add Churches to the Map Legend
12 | Deleting of Listings | When traders wishes to delete a certain listing, the website deletes the incorrect listing.
13 | Remove Google+ share link | Replace with Instagram Share Link | https://www.instagram.com/lets_trade_goods/
14 | Trader Emails | Add hyperlink in trader emails that leads them back to their dashboard
15 | Parent Emails | Parents should be able to monitor their childs activity with email alerts | Child has posted a listing
Deal is finalised with all details
Parents should be able to deactivate their childs listings if not allowed
16 | Categories | Catgories to appear in alphabetical order on categories page and in search box
17 | Trade Details | Fix information that needs to be pulled through
18 | Rating of the trade | Both the Buyer and the Seller needs to rate the trade, at this stage only the buyer can rate the Trader (Seller)
19 | Trader rating | If trader get's a 1-star rating, 3 consecutive times, they need to be banned from the site
20 | Adverts | Advertisements does not appear in the position set up on the back-end, or appear as a broken link. | If the problem is the size of the advert, it should state somewhere the size and type of image needed for the advertisement. | Size of images I've used for test was greater than 800 pixels and it was saved as a PNG image.